## sheet
DFM Feedback Report
Level
|  |  | HOT | Manufacturing or Reliability show stopper
|  |  | WARM | Large impact on cost, quality or cycle time
|  |  | COOL | Low impact on cost, quality or cycle time
Project name:Bebl_v2
Item | Problem Description | Proposed Solution |  | Customer comment | Level | Status
1 | The via hole diameter is 0.6mm, and it is too large, suggest to adjust to 0.4mm | Recommend to adjust all the via holes diameter to 0.4mm |  | OK, DONE, Fresh Gerbers will be sent | WARM | Open
2 | Is the silk screen with the entire frame the positive side? | Please help to confirm. |  | YES | WARM | Open
3 | Is there any height requirement of the LED pin? How much we should remain above the solder? | Please help to confirm. |  | LED should be flush with the PCB | WARM | Open
4 | Please fill in the attached PCB technology file. It is very useful for PCB production | Please fill in the attached PCB technology file. |  | DONE | WARM
5 | There are 2 parts (P7 and U3) could be substitued, the recommend parts have the same performance parameter and less purchase risk and short leadtime. | please kindly check the attached datasheet in the mail, are they OK to be substitued? P7: SMD Micro USB-without POST-W/P,5+4-0.65-L7.4*W5.0*H2.35mm U3: ETA3406 |  | P7 : SMD MICRO USB = OK (we have modified the Gerber file with the new footprint) U3 : NOT OK TPS61221DCK is BOOST Converter ETA3406 is STEP-DOWN Also, they are not pin-compatible | COOL | Open